## Sent & Recived Check list
METAL FABRICATION SUBMISSION AND RECEIPT CHECKLIST (pls. use your initials)
|  | Ring joint file name | file checked | finished part received | Flower joint file name | file checked | finished part received | Vertical Reinforcement | file checked | finished part received | Platform connection | file checked | finished part received | Tube Label | Target Bolt to Bolt Length (m) | Tube received and Verified
1 | A00 | A00 RG 3 |  |  | A00 FJ 3 | [5 empty] | A00 RG 3 |  |  | A00D17 | 0.62711
2 | B00 | B00 RG 3 |  |  | B00 FJ 3 | [8 empty] | A01D18 | 0.60845
3 | C00 | C00 RG 3 |  |  | C00 FJ 3 | [8 empty] | A02D19 | 0.60276
4 | D00 | D00 RG 3 |  |  | D00 FJ 3 | [8 empty] | A03D20 | 0.60146
5 | A01 | A01 RG 3 |  |  | A01 FJ 3 | [5 empty] | A01 RG 3 |  |  | A04D21 | 0.58506
6 | B01 | B01 RG 3 |  |  | B01 FJ 3 | [8 empty] | A05D22 | 0.57728
7 | C01 | C01 RG 3 |  |  | C01 FJ 3 | [8 empty] | A06D23 | 0.56576
8 | D01 | D01 RG 3 |  |  | D01 FJ 3 | [8 empty] | A07D24 | 0.57295
9 | A02 | A02 RG 3 |  |  | A02 FJ 3 | [5 empty] | A02 RG 3 |  |  | A08D25 | 0.54048
10 | B02 | B02 RG 3 |  |  | B02 FJ 3 | [8 empty] | A09D26 | 0.50985
11 | C02 | C02 RG 3 |  |  | C02 FJ 3 | [8 empty] | A10D27 | 0.53702
12 | D02 | D02 RG 3 |  |  | D02 FJ 3 | [8 empty] | A11D28 | 0.56831
13 | A03 | A03 RG 3 |  |  | A03 FJ 3 | [5 empty] | A03 RG 3 |  |  | A12D29 | 0.60362
14 | B03 | B03 RG 3 |  |  | B03 FJ 3 | [8 empty] | A13D30 | 0.64426
15 | C03 | C03 RG 3 |  |  | C03 FJ 3 | [8 empty] | A14D31 | 0.68468
16 | D03 | D03 RG 3 |  |  | D03 FJ 3 | [8 empty] | A15D32 | 0.69304
17 | A04 | A04 RG 3 |  |  | A04 FJ 3 |  |  | A04 RG 3 |  |  | A04 PC 3 |  |  | A16D33 | 0.67426
18 | B04 | B04 RG 3 |  |  | B04 FJ 3 |  |  | B04 RG 3 | [5 empty] | A17D34 | 0.66212
19 | C04 | C04 RG 3 |  |  | C04 FJ 3 |  |  | C04 RG 3 | [5 empty] | A18D00 | 0.68386
20 | D04 | D04 RG 3 |  |  | D04 FJ 3 |  |  | D04 RG 3 | [5 empty] | A19D01 | 0.67966
21 | A05 | A05 RG 3 |  |  | A05 FJ 3 |  |  | A05 RG 3 |  |  | A05 RG 3 |  |  | A20D02 | 0.68044
22 | B05 | B05 RG 3 |  |  | B05 FJ 3 |  |  | B05 RG 3 | [5 empty] | A21D03 | 0.7073
23 | C05 | C05 RG 3 |  |  | C05 FJ 3 |  |  | C05 RG 3 | [5 empty] | A22D04 | 0.58471
24 | D05 | D05 RG 3 |  |  | D05 FJ 3 |  |  | D05 RG 3 | [5 empty] | A23D05 | 0.51619
25 | A06 | A06 RG 3 |  |  | A06 FJ 3 |  |  | A06 RG 3 |  |  | A06 RG 3 |  |  | A24D06 | 0.46268
26 | B06 | B06 RG 3 |  |  | B06 FJ 3 |  |  | B06 RG 3 | [5 empty] | A25D07 | 0.37465
27 | C06 | C06 RG 3 |  |  | C06 FJ 3 |  |  | C06 RG 3 | [5 empty] | A26D08 | 0.31065
28 | D06 | D06 RG 3 |  |  | D06 FJ 3 |  |  | D06 RG 3 | [5 empty] | A27D09 | 0.29582
29 | A07 | A07 RG 3 |  |  | A07 FJ 3 | [8 empty] | A28D10 | 0.30489
30 | B07 | B07 RG 3 |  |  | B07 FJ 3 | [8 empty] | A29D11 | 0.36265
31 | C07 | C07 RG 3 |  |  | C07 FJ 3 | [8 empty] | A30D12 | 0.47162
32 | D07 | D07 RG 3 |  |  | D07 FJ 3 | [8 empty] | A31D13 | 0.42337
33 | A08 | A08 RG 3 |  |  | A08 FJ 3 | [8 empty] | A32D14 | 0.47652
34 | B08 | B08 RG 3 |  |  | B08 FJ 3 | [8 empty] | A33D15 | 0.59589
35 | C08 | C08 RG 3 |  |  | C08 FJ 3 | [8 empty] | A34D16 | 0.59461
36 | D08 | D08 RG 3 |  |  | D08 FJ 3 | [8 empty] | B00C17 | 0.8978
37 | A09 | A09 RG 3 |  |  | A09 FJ 3 | [8 empty] | B00D18 | 0.76781
38 | B09 | B09 RG 3 |  |  | B09 FJ 3 | [8 empty] | B01C18 | 0.86775
39 | C09 | C09 RG 3 |  |  | C09 FJ 3 | [8 empty] | B01D19 | 0.74294
40 | D09 | D09 RG 3 |  |  | D09 FJ 3 | [8 empty] | B02C19 | 0.85541
41 | A10 | A10 RG 3 |  |  | A10 FJ 3 | [8 empty] | B02D20 | 0.72701
42 | B10 | B10 RG 3 |  |  | B10 FJ 3 | [8 empty] | B03C20 | 0.85918
43 | C10 | C10 RG 3 |  |  | C10 FJ 3 | [8 empty] | B03D21 | 0.72698
44 | D10 | D10 RG 3 |  |  | D10 FJ 3 | [8 empty] | B04C21 | 0.81378
45 | A11 | A11 RG 3 |  |  | A11 FJ 3 | [8 empty] | B04D22 | 0.7237
46 | B11 | B11 RG 3 |  |  | B11 FJ 3 | [8 empty] | B05C22 | 0.79164
47 | C11 | C11 RG 3 |  |  | C11 FJ 3 | [8 empty] | B05D23 | 0.70084
48 | D11 | D11 RG 3 |  |  | D11 FJ 3 | [8 empty] | B06C23 | 0.78157
49 | A12 | A12 RG 5 |  |  | A12 FJ 5 | [8 empty] | B06D24 | 0.62863
50 | B12 | B12 RG 5 |  |  | B12 FJ 5 | [8 empty] | B07C24 | 0.75734
51 | C12 | C12 RG 5 |  |  | C12 FJ 5 | [8 empty] | B07D25 | 0.59395
52 | D12 | D12 RG 5 |  |  | D12 FJ 5 | [8 empty] | B08C25 | 0.68839
53 | A13 | A13 RG 3 |  |  | A13 FJ 3 | [8 empty] | B08D26 | 0.511
54 | B13 | B13 RG 3 |  |  | B13 FJ 3 | [8 empty] | B09C26 | 0.6088
55 | C13 | C13 RG 3 |  |  | C13 FJ 3 | [8 empty] | B09D27 | 0.49243
56 | D13 | D13 RG 3 |  |  | D13 FJ 3 | [8 empty] | B10C27 | 0.59281
57 | A14 | A14 RG 3 |  |  | A14 FJ 3 | [8 empty] | B10D28 | 0.51523
58 | B14 | B14 RG 3 |  |  | B14 FJ 3 | [8 empty] | B11C28 | 0.60662
59 | C14 | C14 RG 3 |  |  | C14 FJ 3 | [8 empty] | B11D29 | 0.5517
60 | D14 | D14 RG 3 |  |  | D14 FJ 3 | [8 empty] | B12C29 | 0.64383
61 | A15 | A15 RG 3 |  |  | A15 FJ 3 |  |  | A15 RG 3 | [5 empty] | B12D30 | 0.58758
62 | B15 | B15 RG 3 |  |  | B15 FJ 3 |  |  | B15 RG 3 | [5 empty] | B13C30 | 0.68775
63 | C15 | C15 RG 3 |  |  | C15 FJ 3 |  |  | C15 RG 3 | [5 empty] | B13D31 | 0.6479
64 | D15 | D15 RG 3 |  |  | D15 FJ 3 |  |  | D15 RG 3 | [5 empty] | B14C31 | 0.75181
65 | A16 | A16 RG 3 |  |  | A16 FJ 3 |  |  | A16 RG 3 | [5 empty] | B14D32 | 0.75886
66 | B16 | B16 RG 3 |  |  | B16 FJ 3 |  |  | B16 RG 3 | [5 empty] | B15C32 | 0.82406
67 | C16 | C16 RG 3 |  |  | C16 FJ 3 |  |  | C16 RG 3 | [5 empty] | B15D33 | 0.77813
68 | D16 | D16 RG 3 |  |  | D16 FJ 3 |  |  | D16 RG 3 |  |  | D16 RG 3 |  |  | B16C33 | 0.86855
69 | A17 | A17 RG 3 |  |  | A17 FJ 3 | [8 empty] | B16D34 | 0.77017
70 | B17 | B17 RG 3 |  |  | B17 FJ 3 | [8 empty] | B17C34 | 0.868
71 | C17 | C17 RG 3 |  |  | C17 FJ 3 | [8 empty] | B17D00 | 0.7784
72 | D17 | D17 RG 3 |  |  | D17 FJ 3 | [5 empty] | D17 RG 3 |  |  | B18C00 | 0.89301
73 | A18 | A18 RG 3 |  |  | A18 FJ 3 | [8 empty] | B18D01 | 0.78254
74 | B18 | B18 RG 3 |  |  | B18 FJ 3 | [8 empty] | B19C01 | 0.90624
75 | C18 | C18 RG 3 |  |  | C18 FJ 3 | [8 empty] | B19D02 | 0.79184
76 | D18 | D18 RG 3 |  |  | D18 FJ 3 | [5 empty] | D18 RG 3 |  |  | B20C02 | 0.89665
77 | A19 | A19 RG 3 |  |  | A19 FJ 3 | [8 empty] | B20D03 | 0.83033
78 | B19 | B19 RG 3 |  |  | B19 FJ 3 | [8 empty] | B21C03 | 0.88111
79 | C19 | C19 RG 3 |  |  | C19 FJ 3 | [8 empty] | B21D04 | 0.63794
80 | D19 | D19 RG 3 |  |  | D19 FJ 3 | [5 empty] | D19 RG 3 |  |  | B22C04 | 0.77741
81 | A20 | A20 RG 3 |  |  | A20 FJ 3 | [8 empty] | B22D05 | 0.56378
82 | B20 | B20 RG 3 |  |  | B20 FJ 3 | [8 empty] | B23C05 | 0.70389
83 | C20 | C20 RG 3 |  |  | C20 FJ 3 | [8 empty] | B23D06 | 0.64098
84 | D20 | D20 RG 3 |  |  | D20 FJ 3 | [5 empty] | D20 RG 3 |  |  | B24C06 | 0.69208
85 | A21 | A21 RG 5 |  |  | A21 FJ 5 | [8 empty] | B24D07 | 0.63839
86 | B21 | B21 RG 5 |  |  | B21 FJ 5 | [8 empty] | B25C07 | 0.68607
87 | C21 | C21 RG 5 |  |  | C21 FJ 5 | [8 empty] | B25D08 | 0.59203
88 | D21 | D21 RG 5 |  |  | D21 FJ 5 | [5 empty] | D21 RG 5 |  |  | B26C08 | 0.65777
89 | A22 | A22 RG 3 |  |  | A22 FJ 3 |  |  | A22 RG 3 | [5 empty] | B26D09 | 0.56385
90 | B22 | B22 RG 3 |  |  | B22 FJ 3 |  |  | B22 RG 3 | [5 empty] | B27C09 | 0.63429
91 | C22 | C22 RG 3 |  |  | C22 FJ 3 |  |  | C22 RG 3 | [5 empty] | B27D10 | 0.53134
92 | D22 | D22 RG 3 |  |  | D22 FJ 3 |  |  | D22 RG 3 |  |  | D22 RG 3 |  |  | B28C10 | 0.59391
93 | A23 | A23 RG 3 |  |  | A23 FJ 3 |  |  | A23 RG 3 | [5 empty] | B28D11 | 0.52619
94 | B23 | B23 RG 3 |  |  | B23 FJ 3 |  |  | B23 RG 3 | [5 empty] | B29C11 | 0.6062
95 | C23 | C23 RG 3 |  |  | C23 FJ 3 |  |  | C23 RG 3 | [5 empty] | B29D12 | 0.61949
96 | D23 | D23 RG 3 |  |  | D23 FJ 3 |  |  | D23 RG 3 |  |  | D23 RG 3 |  |  | B30C12 | 0.70386
97 | A24 | A24 RG 3 |  |  | A24 FJ 3 | [8 empty] | B30D13 | 0.69262
98 | B24 | B24 RG 3 |  |  | B24 FJ 3 | [8 empty] | B31C13 | 0.70059
99 | C24 | C24 RG 3 |  |  | C24 FJ 3 | [8 empty] | B31D14 | 0.68836
100 | D24 | D24 RG 3 |  |  | D24 FJ 3 | [5 empty] | D24 RG 3 |  |  | B32C14 | 0.81223
101 | A25 | A25 RG 3 |  |  | A25 FJ 3 | [8 empty] | B32D15 | 0.73516
102 | B25 | B25 RG 3 |  |  | B25 FJ 3 | [8 empty] | B33C15 | 0.89622
103 | C25 | C25 RG 3 |  |  | C25 FJ 3 | [8 empty] | B33D16 | 0.76874
104 | D25 | D25 RG 3 |  |  | D25 FJ 3 | [8 empty] | B34C16 | 0.88669
105 | A26 | A26 RG 3 |  |  | A26 FJ 3 | [8 empty] | B34D17 | 0.74921
106 | B26 | B26 RG 3 |  |  | B26 FJ 3 | [8 empty] | C00B17 | 0.91743
107 | C26 | C26 RG 3 |  |  | C26 FJ 3 | [8 empty] | C00C18 | 0.91015
108 | D26 | D26 RG 3 |  |  | D26 FJ 3 | [8 empty] | C01B18 | 0.88654
109 | A27 | A27 RG 3 |  |  | A27 FJ 3 | [8 empty] | C01C19 | 0.87787
110 | B27 | B27 RG 3 |  |  | B27 FJ 3 | [8 empty] | C02B19 | 0.88286
111 | C27 | C27 RG 3 |  |  | C27 FJ 3 | [8 empty] | C02C20 | 0.86337
112 | D27 | D27 RG 3 |  |  | D27 FJ 3 | [8 empty] | C03B20 | 0.92956
113 | A28 | A28 RG 3 |  |  | A28 FJ 3 | [8 empty] | C03C21 | 0.85967
114 | B28 | B28 RG 3 |  |  | B28 FJ 3 | [8 empty] | C04B21 | 0.86958
115 | C28 | C28 RG 3 |  |  | C28 FJ 3 | [8 empty] | C04C22 | 0.85907
116 | D28 | D28 RG 3 |  |  | D28 FJ 3 | [8 empty] | C05B22 | 0.79342
117 | A29 | A29 RG 3 |  |  | A29 FJ 3 | [8 empty] | C05C23 | 0.78994
118 | B29 | B29 RG 3 |  |  | B29 FJ 3 | [8 empty] | C06B23 | 0.70509
119 | C29 | C29 RG 3 |  |  | C29 FJ 3 | [8 empty] | C06C24 | 0.70671
120 | D29 | D29 RG 3 |  |  | D29 FJ 3 | [8 empty] | C07B24 | 0.62921
121 | A30 | A30 RG 3 |  |  | A30 FJ 3 | [8 empty] | C07C25 | 0.64271
122 | B30 | B30 RG 3 |  |  | B30 FJ 3 | [8 empty] | C08B25 | 0.54869
123 | C30 | C30 RG 3 |  |  | C30 FJ 3 | [8 empty] | C08C26 | 0.55722
124 | D30 | D30 RG 3 |  |  | D30 FJ 3 | [8 empty] | C09B26 | 0.48123
125 | A31 | A31 RG 3 |  |  | A31 FJ 3 | [8 empty] | C09C27 | 0.50709
126 | B31 | B31 RG 3 |  |  | B31 FJ 3 | [8 empty] | C10B27 | 0.4689
127 | C31 | C31 RG 3 |  |  | C31 FJ 3 | [8 empty] | C10C28 | 0.50548
128 | D31 | D31 RG 3 |  |  | D31 FJ 3 | [8 empty] | C11B28 | 0.47856
129 | A32 | A32 RG 3 |  |  | A32 FJ 3 | [8 empty] | C11C29 | 0.52599
130 | B32 | B32 RG 3 |  |  | B32 FJ 3 | [8 empty] | C12B29 | 0.51196
131 | C32 | C32 RG 3 |  |  | C32 FJ 3 | [8 empty] | C12C30 | 0.56373
132 | D32 | D32 RG 3 |  |  | D32 FJ 3 | [8 empty] | C13B30 | 0.53311
133 | A33 | A33 RG 3 |  |  | A33 FJ 3 |  |  | A33 RG 3 | [5 empty] | C13C31 | 0.57665
134 | B33 | B33 RG 3 |  |  | B33 FJ 3 |  |  | B33 RG 3 | [5 empty] | C14B31 | 0.57526
135 | C33 | C33 RG 3 |  |  | C33 FJ 3 |  |  | C33 RG 3 | [5 empty] | C14C32 | 0.70319
136 | D33 | D33 RG 3 |  |  | D33 FJ 3 |  |  | D33 RG 3 | [5 empty] | C15B32 | 0.70756
137 | A34 | A34 RG 3 |  |  | A34 FJ 3 |  |  | A34 RG 3 | [5 empty] | C15C33 | 0.83136
138 | B34 | B34 RG 3 |  |  | B34 FJ 3 |  |  | B34 RG 3 | [5 empty] | C16B33 | 0.84053
139 | C34 | C34 RG 3 |  |  | C34 FJ 3 |  |  | C34 RG 3 | [5 empty] | C16C34 | 0.85393
140 | D34 | D34 RG 3 |  |  | D34 FJ 3 |  |  | D34 RG 3 | [5 empty] | C17B34 | 0.84511
[14 empty] | C17C00 | 0.87982
[14 empty] | C18B00 | 0.87902
[14 empty] | C18C01 | 0.88109
[14 empty] | C19B01 | 0.87978
[14 empty] | C19C02 | 0.8924
[14 empty] | C20B02 | 0.86339
[14 empty] | C20C03 | 0.92432
[14 empty] | C21B03 | 0.83323
[14 empty] | C21C04 | 0.79511
[14 empty] | C22B04 | 0.76358
[14 empty] | C22C05 | 0.63798
[14 empty] | C23B05 | 0.76859
[14 empty] | C23C06 | 0.6645
[14 empty] | C24B06 | 0.77051
[14 empty] | C24C07 | 0.72755
[14 empty] | C25B07 | 0.79639
[14 empty] | C25C08 | 0.71685
[14 empty] | C26B08 | 0.7718
[14 empty] | C26C09 | 0.70713
[14 empty] | C27B09 | 0.77932
[14 empty] | C27C10 | 0.68869
[14 empty] | C28B10 | 0.74562
[14 empty] | C28C11 | 0.66287
[14 empty] | C29B11 | 0.73938
[14 empty] | C29C12 | 0.71044
[14 empty] | C30B12 | 0.78933
[14 empty] | C30C13 | 0.78382
[14 empty] | C31B13 | 0.77577
[14 empty] | C31C14 | 0.82277
[14 empty] | C32B14 | 0.83163
[14 empty] | C32C15 | 0.87079
[14 empty] | C33B15 | 0.9007
[14 empty] | C33C16 | 0.90984
[14 empty] | C34B16 | 0.91169
[14 empty] | C34C17 | 0.89741
[14 empty] | D00A17 | 0.67195
[14 empty] | D00B18 | 0.81377
[14 empty] | D01A18 | 0.66168
[14 empty] | D01B19 | 0.78576
[14 empty] | D02A19 | 0.66947
[14 empty] | D02B20 | 0.77714
[14 empty] | D03A20 | 0.73475
[14 empty] | D03B21 | 0.77451
[14 empty] | D04A21 | 0.59758
[14 empty] | D04B22 | 0.74161
[14 empty] | D05A22 | 0.50856
[14 empty] | D05B23 | 0.72679
[14 empty] | D06A23 | 0.48794
[14 empty] | D06B24 | 0.66562
[14 empty] | D07A24 | 0.42055
[14 empty] | D07B25 | 0.56912
[14 empty] | D08A25 | 0.33884
[14 empty] | D08B26 | 0.48442
[14 empty] | D09A26 | 0.30112
[14 empty] | D09B27 | 0.44028
[14 empty] | D10A27 | 0.30034
[14 empty] | D10B28 | 0.44177
[14 empty] | D11A28 | 0.33278
[14 empty] | D11B29 | 0.46901
[14 empty] | D12A29 | 0.43392
[14 empty] | D12B30 | 0.52317
[14 empty] | D13A30 | 0.48133
[14 empty] | D13B31 | 0.45784
[14 empty] | D14A31 | 0.46243
[14 empty] | D14B32 | 0.51704
[14 empty] | D15A32 | 0.52982
[14 empty] | D15B33 | 0.68233
[14 empty] | D16A33 | 0.61066
[14 empty] | D16B34 | 0.71166
[14 empty] | D17A34 | 0.59795
[14 empty] | D17B00 | 0.75034
[14 empty] | D18A00 | 0.63316
[14 empty] | D18B01 | 0.74094
[14 empty] | D19A01 | 0.61428
[14 empty] | D19B02 | 0.74863
[14 empty] | D20A02 | 0.59657
[14 empty] | D20B03 | 0.76265
[14 empty] | D21A03 | 0.59326
[14 empty] | D21B04 | 0.73084
[14 empty] | D22A04 | 0.58078
[14 empty] | D22B05 | 0.65032
[14 empty] | D23A05 | 0.59119
[14 empty] | D23B06 | 0.59135
[14 empty] | D24A06 | 0.56272
[14 empty] | D24B07 | 0.62777
[14 empty] | D25A07 | 0.56988
[14 empty] | D25B08 | 0.63067
[14 empty] | D26A08 | 0.51188
[14 empty] | D26B09 | 0.63617
[14 empty] | D27A09 | 0.53164
[14 empty] | D27B10 | 0.64744
[14 empty] | D28A10 | 0.55731
[14 empty] | D28B11 | 0.63407
[14 empty] | D29A11 | 0.58927
[14 empty] | D29B12 | 0.65047
[14 empty] | D30A12 | 0.61985
[14 empty] | D30B13 | 0.699
[14 empty] | D31A13 | 0.64537
[14 empty] | D31B14 | 0.74991
[14 empty] | D32A14 | 0.6925
[14 empty] | D32B15 | 0.78495
[14 empty] | D33A15 | 0.68023
[14 empty] | D33B16 | 0.80781
[14 empty] | D34A16 | 0.66794
[14 empty] | D34B17 | 0.79807
Vertical Tubes

## CNC Check List
CNC CHECKLIST (pls. use your initials)
Rib Label | Side 0 CNC'ed | Side 1 CNC'ed | 2 Sides Laminated | Moiré Label | Left Segment CNC'ed | Center Segment CNC'ed | Right Segment CNC'ed | Moiré Laminated | Triangle Joint Label | Flat CNC'ed | Rib Connection CNC'ed | Bolt Holes Drilled
A00A01 |  |  |  | 1 |  |  |  |  | 1
A01A02 |  |  |  | 2 |  |  |  |  | 2
A02A03 |  |  |  | 3 |  |  |  |  | 3
A03A04 |  |  |  | 4 |  |  |  |  | 4
A04A05 |  |  |  | 5 |  |  |  |  | 5
A05A06 |  |  |  | 6 |  |  |  |  | 6
A06A07 |  |  |  | 7 |  |  |  |  | 7
A07A08 |  |  |  | 8 |  |  |  |  | 8
A08A09 |  |  |  | 9 |  |  |  |  | 9
A09A10 |  |  |  | 10 |  |  |  |  | 10
A10A11 |  |  |  | 11 |  |  |  |  | 11
A11A12 |  |  |  | 12 |  |  |  |  | 12
A12A13 |  |  |  | 13 |  |  |  |  | 13
A13A14 |  |  |  | 14 |  |  |  |  | 14
A14A15 |  |  |  | 15 |  |  |  |  | 15
A15A16 |  |  |  | 16 |  |  |  |  | 16
A16A17 |  |  |  | 17 |  |  |  |  | 17
A17A18 |  |  |  | 18 |  |  |  |  | 18
A18A19 |  |  |  | 19 |  |  |  |  | 19
A19A20 |  |  |  | 20 |  |  |  |  | 20
A20A21 |  |  |  | 21 |  |  |  |  | 21
A21A22 |  |  |  | 22 |  |  |  |  | 22
A22A23 |  |  |  | 23 |  |  |  |  | 23
A23A24 |  |  |  | 24 |  |  |  |  | 24
A24A25 |  |  |  | 25 |  |  |  |  | 25
A25A26 |  |  |  | 26 |  |  |  |  | 26
A26A27 |  |  |  | 27 |  |  |  |  | 27
A27A28 |  |  |  | 28 |  |  |  |  | 28
A28A29 |  |  |  | 29 |  |  |  |  | 29
A29A30 |  |  |  | 30 |  |  |  |  | 30
A30A31 |  |  |  | 31 |  |  |  |  | 31
A31A32 |  |  |  | 32 |  |  |  |  | 32
A32A33 |  |  |  | 33 |  |  |  |  | 33
A33A34 |  |  |  | 34 |  |  |  |  | 34
A34A00 |  |  |  | 35 |  |  |  |  | 35
B00B01 |  |  |  | 36 |  |  |  |  | 36
B01B02 |  |  |  | 37 |  |  |  |  | 37
B02B03 |  |  |  | 38 |  |  |  |  | 38
B03B04 |  |  |  | 39 |  |  |  |  | 39
B04B05 |  |  |  | 40 |  |  |  |  | 40
B05B06 |  |  |  | 41 |  |  |  |  | 41
B06B07 |  |  |  | 42 |  |  |  |  | 42
B07B08 |  |  |  | 43 |  |  |  |  | 43
B08B09 |  |  |  | 44 |  |  |  |  | 44
B09B10 |  |  |  | 45 |  |  |  |  | 45
B10B11 |  |  |  | 46 |  |  |  |  | 46
B11B12 |  |  |  | 47 |  |  |  |  | 47
B12B13 |  |  |  | 48 |  |  |  |  | 48
B13B14 |  |  |  | 49 |  |  |  |  | 49
B14B15 |  |  |  | 50 |  |  |  |  | 50
B15B16 |  |  |  | 51 |  |  |  |  | 51
B16B17 |  |  |  | 52 |  |  |  |  | 52
B17B18 |  |  |  | 53 |  |  |  |  | 53
B18B19 |  |  |  | 54 |  |  |  |  | 54
B19B20 |  |  |  | 55 |  |  |  |  | 55
B20B21 |  |  |  | 56 |  |  |  |  | 56
B21B22 |  |  |  | 57 |  |  |  |  | 57
B22B23 |  |  |  | 58 |  |  |  |  | 58
B23B24 |  |  |  | 59 |  |  |  |  | 59
B24B25 |  |  |  | 60 |  |  |  |  | 60
B25B26 |  |  |  | 61 |  |  |  |  | 61
B26B27 |  |  |  | 62 |  |  |  |  | 62
B27B28 |  |  |  | 63 |  |  |  |  | 63
B28B29 |  |  |  | 64 |  |  |  |  | 64
B29B30 |  |  |  | 65 |  |  |  |  | 65
B30B31 |  |  |  | 66 |  |  |  |  | 66
B31B32 |  |  |  | 67 |  |  |  |  | 67
B32B33 |  |  |  | 68 |  |  |  |  | 68
B33B34 |  |  |  | 69 |  |  |  |  | 69
B34B00 |  |  |  | 70 |  |  |  |  | 70
C00C01 |  |  |  | 71 |  |  |  |  | 71
C01C02 |  |  |  | 72 |  |  |  |  | 72
C02C03 |  |  |  | 73 |  |  |  |  | 73
C03C04 |  |  |  | 74 |  |  |  |  | 74
C04C05 |  |  |  | 75 |  |  |  |  | 75
C05C06 |  |  |  | 76 |  |  |  |  | 76
C06C07 |  |  |  | 77 |  |  |  |  | 77
C07C08 |  |  |  | 78 |  |  |  |  | 78
C08C09 |  |  |  | 79 |  |  |  |  | 79
C09C10 |  |  |  | 80 |  |  |  |  | 80
C10C11 |  |  |  | 81 |  |  |  |  | 81
C11C12 |  |  |  | 82 |  |  |  |  | 82
C12C13 |  |  |  | 83 |  |  |  |  | 83
C13C14 |  |  |  | 84 |  |  |  |  | 84
C14C15 |  |  |  | 85 |  |  |  |  | 85
C15C16 |  |  |  | 86 |  |  |  |  | 86
C16C17 |  |  |  | 87 |  |  |  |  | 87
C17C18 |  |  |  | 88 |  |  |  |  | 88
C18C19 |  |  |  | 89 |  |  |  |  | 89
C19C20 |  |  |  | 90 |  |  |  |  | 90
C20C21 |  |  |  | 91 |  |  |  |  | 91
C21C22 |  |  |  | 92 |  |  |  |  | 92
C22C23 |  |  |  | 93 |  |  |  |  | 93
C23C24 |  |  |  | 94 |  |  |  |  | 94
C24C25 |  |  |  | 95 |  |  |  |  | 95
C25C26 |  |  |  | 96 |  |  |  |  | 96
C26C27 |  |  |  | 97 |  |  |  |  | 97
C27C28 |  |  |  | 98 |  |  |  |  | 98
C28C29 |  |  |  | 99 |  |  |  |  | 99
C29C30 |  |  |  | 100 |  |  |  |  | 100
C30C31 |  |  |  | 101 |  |  |  |  | 101
C31C32 |  |  |  | 102 |  |  |  |  | 102
C32C33 |  |  |  | 103 |  |  |  |  | 103
C33C34 |  |  |  | 104 |  |  |  |  | 104
C34C00 |  |  |  | 105 |  |  |  |  | 105
D00D01 |  |  |  | 106 |  |  |  |  | 106
D01D02 |  |  |  | 107 |  |  |  |  | 107
D02D03 |  |  |  | 108 |  |  |  |  | 108
D03D04 |  |  |  | 109 |  |  |  |  | 109
D04D05 |  |  |  | 110 |  |  |  |  | 110
D05D06 |  |  |  | 111 |  |  |  |  | 111
D06D07 |  |  |  | 112 |  |  |  |  | 112
D07D08 |  |  |  | 113 |  |  |  |  | 113
D08D09 |  |  |  | 114 |  |  |  |  | 114
D09D10 |  |  |  | 115 |  |  |  |  | 115
D10D11 |  |  |  | 116 |  |  |  |  | 116
D11D12 |  |  |  | 117 |  |  |  |  | 117
D12D13 |  |  |  | 118 |  |  |  |  | 118
D13D14 |  |  |  | 119 |  |  |  |  | 119
D14D15 |  |  |  | 120 |  |  |  |  | 120
D15D16 |  |  |  | 121 |  |  |  |  | 121
D16D17 |  |  |  | 122 |  |  |  |  | 122
D17D18 |  |  |  | 123 |  |  |  |  | 123
D18D19 |  |  |  | 124 |  |  |  |  | 124
D19D20 |  |  |  | 125 |  |  |  |  | 125
D20D21 |  |  |  | 126 |  |  |  |  | 126
D21D22 |  |  |  | 127 |  |  |  |  | 127
D22D23 |  |  |  | 128 |  |  |  |  | 128
D23D24 |  |  |  | 129 |  |  |  |  | 129
D24D25 |  |  |  | 130 |  |  |  |  | 130
D25D26 |  |  |  | 131 |  |  |  |  | 131
D26D27 |  |  |  | 132 |  |  |  |  | 132
D27D28 |  |  |  | 133 |  |  |  |  | 133
D28D29 |  |  |  | 134 |  |  |  |  | 134
D29D30 |  |  |  | 135 |  |  |  |  | 135
D30D31 |  |  |  | 136 |  |  |  |  | 136
D31D32 |  |  |  | 137 |  |  |  |  | 137
D32D33 |  |  |  | 138 |  |  |  |  | 138
D33D34 |  |  |  | 139 |  |  |  |  | 139
D34D00 |  |  |  | 140 |  |  |  |  | 140
|  |  |  | 141 |  |  |  |  | 141
|  |  |  | 142 |  |  |  |  | 142
|  |  |  | 143 |  |  |  |  | 143
|  |  |  | 144 |  |  |  |  | 144
|  |  |  | 145 |  |  |  |  | 145
|  |  |  | 146 |  |  |  |  | 146
|  |  |  | 147 |  |  |  |  | 147
|  |  |  | 148 |  |  |  |  | 148
|  |  |  | 149 |  |  |  |  | 149
|  |  |  | 150 |  |  |  |  | 150
|  |  |  | 151 |  |  |  |  | 151
|  |  |  | 152 |  |  |  |  | 152
|  |  |  | 153 |  |  |  |  | 153
|  |  |  | 154 |  |  |  |  | 154
|  |  |  | 155 |  |  |  |  | 155
|  |  |  | 156 |  |  |  |  | 156
|  |  |  | 157 |  |  |  |  | 157
|  |  |  | 158 |  |  |  |  | 158
|  |  |  | 159 |  |  |  |  | 159
|  |  |  | 160 |  |  |  |  | 160
|  |  |  | 161 |  |  |  |  | 161
|  |  |  | 162 |  |  |  |  | 162
|  |  |  | 163 |  |  |  |  | 163
|  |  |  | 164 |  |  |  |  | 164
|  |  |  | 165 |  |  |  |  | 165
|  |  |  | 166 |  |  |  |  | 166
|  |  |  | 167 |  |  |  |  | 167
|  |  |  | 168 |  |  |  |  | 168
|  |  |  | 169 |  |  |  |  | 169
|  |  |  | 170 |  |  |  |  | 170
|  |  |  | 171 |  |  |  |  | 171
|  |  |  | 172 |  |  |  |  | 172
|  |  |  | 173 |  |  |  |  | 173
|  |  |  | 174 |  |  |  |  | 174
|  |  |  | 175 |  |  |  |  | 175
|  |  |  | 176 |  |  |  |  | 176
|  |  |  | 177 |  |  |  |  | 177
|  |  |  | 178 |  |  |  |  | 178
|  |  |  | 179 |  |  |  |  | 179
|  |  |  | 180 |  |  |  |  | 180
|  |  |  | 181 |  |  |  |  | 181
|  |  |  | 182 |  |  |  |  | 182
|  |  |  | 183 |  |  |  |  | 183
|  |  |  | 184 |  |  |  |  | 184
|  |  |  | 185 |  |  |  |  | 185
|  |  |  | 186 |  |  |  |  | 186
|  |  |  | 187 |  |  |  |  | 187
|  |  |  | 188 |  |  |  |  | 188
|  |  |  | 189 |  |  |  |  | 189
|  |  |  | 190 |  |  |  |  | 190
|  |  |  | 191 |  |  |  |  | 191
|  |  |  | 192 |  |  |  |  | 192
|  |  |  | 193 |  |  |  |  | 193
|  |  |  | 194 |  |  |  |  | 194
|  |  |  | 195 |  |  |  |  | 195
|  |  |  | 196 |  |  |  |  | 196
|  |  |  | 197 |  |  |  |  | 197
|  |  |  | 198 |  |  |  |  | 198
|  |  |  | 199 |  |  |  |  | 199
|  |  |  | 200 |  |  |  |  | 200
|  |  |  | 201 |  |  |  |  | 201
|  |  |  | 202 |  |  |  |  | 202
|  |  |  | 203 |  |  |  |  | 203
|  |  |  | 204 |  |  |  |  | 204
|  |  |  | 205 |  |  |  |  | 205
|  |  |  | 206 |  |  |  |  | 206
|  |  |  | 207 |  |  |  |  | 207
|  |  |  | 208 |  |  |  |  | 208
|  |  |  | 209 |  |  |  |  | 209
|  |  |  | 210 |  |  |  |  | 210
|  |  |  | 211 |  |  |  |  | 211
|  |  |  | 212 |  |  |  |  | 212
|  |  |  | 213 |  |  |  |  | 213
|  |  |  | 214 |  |  |  |  | 214
|  |  |  | 215 |  |  |  |  | 215
|  |  |  | 216 |  |  |  |  | 216
|  |  |  | 217 |  |  |  |  | 217
|  |  |  | 218 |  |  |  |  | 218
|  |  |  | 219 |  |  |  |  | 219
|  |  |  | 220 |  |  |  |  | 220
|  |  |  | 221 |  |  |  |  | 221
|  |  |  | 222 |  |  |  |  | 222
|  |  |  | 223 |  |  |  |  | 223
|  |  |  | 224 |  |  |  |  | 224
|  |  |  | 225 |  |  |  |  | 225
|  |  |  | 226 |  |  |  |  | 226
|  |  |  | 227 |  |  |  |  | 227
|  |  |  | 228 |  |  |  |  | 228
|  |  |  | 229 |  |  |  |  | 229
|  |  |  | 230 |  |  |  |  | 230
|  |  |  | 231 |  |  |  |  | 231
|  |  |  | 232 |  |  |  |  | 232
|  |  |  | 233 |  |  |  |  | 233
|  |  |  | 234 |  |  |  |  | 234
|  |  |  | 235 |  |  |  |  | 235
|  |  |  | 236 |  |  |  |  | 236
|  |  |  | 237 |  |  |  |  | 237
|  |  |  | 238 |  |  |  |  | 238
|  |  |  | 239 |  |  |  |  | 239
|  |  |  | 240 |  |  |  |  | 240
|  |  |  | 241 |  |  |  |  | 241
|  |  |  | 242 |  |  |  |  | 242
|  |  |  | 243 |  |  |  |  | 243
|  |  |  | 244 |  |  |  |  | 244
|  |  |  | 245 |  |  |  |  | 245
|  |  |  | 246 |  |  |  |  | 246
|  |  |  | 247 |  |  |  |  | 247
|  |  |  | 248 |  |  |  |  | 248
|  |  |  | 249 |  |  |  |  | 249
|  |  |  | 250 |  |  |  |  | 250
|  |  |  | 251 |  |  |  |  | 251
|  |  |  | 252 |  |  |  |  | 252
|  |  |  | 253 |  |  |  |  | 253
|  |  |  | 254 |  |  |  |  | 254
|  |  |  | 255 |  |  |  |  | 255
|  |  |  | 256 |  |  |  |  | 256
|  |  |  | 257 |  |  |  |  | 257
|  |  |  | 258 |  |  |  |  | 258
|  |  |  | 259 |  |  |  |  | 259
|  |  |  | 260 |  |  |  |  | 260
|  |  |  | 261 |  |  |  |  | 261
|  |  |  | 262 |  |  |  |  | 262
|  |  |  | 263 |  |  |  |  | 263
|  |  |  | 264 |  |  |  |  | 264
|  |  |  | 265 |  |  |  |  | 265
|  |  |  | 266 |  |  |  |  | 266
|  |  |  | 267 |  |  |  |  | 267
|  |  |  | 268 |  |  |  |  | 268
|  |  |  | 269 |  |  |  |  | 269
|  |  |  | 270 |  |  |  |  | 270
|  |  |  | 271 |  |  |  |  | 271
|  |  |  | 272 |  |  |  |  | 272
|  |  |  | 273 |  |  |  |  | 273
|  |  |  | 274 |  |  |  |  | 274
|  |  |  | 275 |  |  |  |  | 275
|  |  |  | 276 |  |  |  |  | 276
|  |  |  | 277 |  |  |  |  | 277
|  |  |  | 278 |  |  |  |  | 278
|  |  |  | 279 |  |  |  |  | 279
|  |  |  | 280 |  |  |  |  | 280
|  |  |  | 281 |  |  |  |  | 281
|  |  |  | 282 |  |  |  |  | 282
|  |  |  | 283 |  |  |  |  | 283
|  |  |  | 284 |  |  |  |  | 284
|  |  |  | 285 |  |  |  |  | 285
|  |  |  | 286 |  |  |  |  | 286
|  |  |  | 287 |  |  |  |  | 287
|  |  |  | 288 |  |  |  |  | 288
|  |  |  | 289 |  |  |  |  | 289
|  |  |  | 290 |  |  |  |  | 290
|  |  |  | 291 |  |  |  |  | 291
|  |  |  | 292 |  |  |  |  | 292
|  |  |  | 293 |  |  |  |  | 293
|  |  |  | 294 |  |  |  |  | 294
|  |  |  | 295 |  |  |  |  | 295
|  |  |  | 296 |  |  |  |  | 296
|  |  |  | 297 |  |  |  |  | 297
|  |  |  | 298 |  |  |  |  | 298
|  |  |  | 299 |  |  |  |  | 299
|  |  |  | 300 |  |  |  |  | 300
|  |  |  | 301 |  |  |  |  | 301
|  |  |  | 302 |  |  |  |  | 302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425
426
427
428
429
430
431
432
433
434
435
436
437
438
439
440
441
442
443
444
445
446
447
448
449
450
451
452
453
454
455
456
457
458
459
460
461
462
463
464
465
466
467
468
469
470
471
472
473
474
475
476
477
478
479
480
481
482
483
484
485
486
487
488
489
490
491
492
493
494
495
496
497
498
499
500
501
502
503
504
505
506
507
508
509
510
511
512
513
514
515
516
517
518
519
520
521
522
523
524
525
526
527
528
529
530
531
532
533
534
535
536
537
538
539
540
541
542
543
544
545
546
547
548
549
550
551
552
553
554
555
556
557
558
559
560
561
562
563
564
565
566
567
568
569
570
571
572
573
574
575
576
577
578
579
580
581
582
583
584
585
586
587
588
589
590
591
592
593
594
595
596
597
598
599
600
601
602
603
604
605
606
607
608
609
610
611
612
613
614
615
616
617
618
619
620
621
622
623
624
625
626
627
628
629
630
631
632
633
634
635
636
637
638
639
640
641
642
643
644
645
646
647
648
649
650
651
652
653
654
655
656
657
658
659
660
661
662
663
664
665
666
667
668
669
670
671
672
673
674
675
676
677
678
679
680
681
682
683
684
685
686
687
688
689
690
691
692
693
694
695
696
697
698
699
700
701
702
703
704
705
706
707
708
709
710
711
712
713
714
715
716
717
718
719
720
721
722
723
724
725
726
727
728
729
730
731
732
733
734
735
736
737
738
739
740
741
742
743
744
745
746
747
748
749
750
751
752
753
754
755
756
757
758
759
760
761
762
763
764
765
766
767
768
769
770
771
772
773
774
775
776
777
778
779
780
781
782
783
784
785
786
787
788
789
790
791
792
793
794
795
796
797
798
799
800
801
802
803
804
805
806
807
808
809
810
811
812
813
814
815
816
817
818
819
820
821
822
823
824
825
826
827
828
829
830
831
832
833
834
835
836
837
838
839
840
841
842
843
844
845
846
847
848
849
850
851
852
853
854
855
856
857
858
859
860
861
862
863
864
865
866
867
868
869
870
871
872
873
874
875
876
877
878
879
880
881
882
883
884
885
886
887
888
889
890
891
892
893
894
895
896
897
898
899
900
901
902
903
904
905
906
907
908
909
910
911
912
913
914
915
916
917
918
919
920
921
922
923
924
925
926
927
928
929
930
931
932
933
934
935
936
937
938
939
940
941
942
943
944
945
946
947
948
949
950
951
952
953
954
955
956
957
958
959
960
961
962
963
964
965
966
967
968
969
970
971
972
973
974
975
976
977
978
979
980
981
982
983
984
985
986
987
988
989
990
991
992
993
994
995
996
997
998
999
1000
1001
1002
1003
1004
1005
1006
1007
1008
1009
1010
1011
1012
1013
1014
1015
1016
1017
1018
1019
1020
1021
1022
1023
1024
1025
1026
1027
1028
1029
1030
1031
1032
1033
1034
1035
1036
1037
1038
1039
1040
1041
1042
1043
1044
1045
1046
1047
1048
1049
1050
1051
1052
1053
1054
1055
1056
1057
1058
1059
1060
1061
1062
1063
1064
1065
1066
1067
1068
1069
1070
1071
1072
1073
1074
1075
1076
1077
1078
1079
1080
1081
1082
1083
1084
1085
1086
1087
1088
1089
1090
1091
1092
1093
1094
1095
1096
1097
1098
1099
1100
1101
1102
1103
1104
1105
1106
1107
1108
1109
1110
1111
1112
1113
1114
1115
1116
1117
1118
1119
1120
1121
1122
1123
1124
1125
1126
1127
1128
1129
1130
1131
1132
1133
1134
1135
1136
1137
1138
1139
1140
1141
1142
1143
1144
1145
1146
1147
1148
1149
1150
1151
1152
1153
1154
1155
1156
1157
1158
1159
1160
1161
1162
1163
1164
1165
1166
1167
1168
1169
1170
1171
1172
1173
1174
1175
1176
1177
1178
1179
1180
1181
1182
1183
1184
1185
1186
1187
1188
1189
1190
1191
1192
1193
1194
1195
1196
1197
1198
1199
1200
1201
1202
1203
1204
1205
1206
1207
1208

## Digital Model Check List
| Flower Joint Verification Check List (pls. use your initials) | [11 empty] | Ring Joint Verification Check List (pls. use your initials)
| Flower Joint | Verify joint is using the correct thickness | Tube Bolt holes A-line with petals | Petals do not physically interfere with tubes | Tubes do not physically interfere with one another. | Flower Joints do not physically interfere with ribs | Verify no Bolt/Washer interference with other bolts/washers or petals or tubes | Verify labels are visible & not overlapping | Verify labeling (flower-to-ring) | Verify labeling (petal-to-next-petal) | Verify no overlapping of text |  | Ring Joint | Verify joint is using the correct thickness | Verify petal-to-next-petal lables match | Verify no overlapping of text | Rib Bolt holes A-line with flaps | No Bolt/Washer interference with other bolts/washers or flaps or tubes | Ring Does not extend beyond outside edge of Rib | Ring Joint connects to Flower with no gap or interference | Ring Joint connects to Flower with no gap or interference | Ring Joints with vertical reinforcement have no gaps or interference (note 1) | Ring Joints with Platform Connection joints have no gaps or interferences (note 2)
| A00 | [11 empty] | A00
| B00 | [11 empty] | B00
| C00 | [11 empty] | C00
| D00 | [11 empty] | D00
| A01 | [11 empty] | A01
| B01 | [11 empty] | B01
| C01 | [11 empty] | C01
| D01 | [11 empty] | D01
| A02 | [11 empty] | A02
| B02 | [11 empty] | B02
| C02 | [11 empty] | C02
| D02 | [11 empty] | D02
| A03 | [11 empty] | A03
| B03 | [11 empty] | B03
| C03 | [11 empty] | C03
| D03 | [11 empty] | D03
| A04 | [11 empty] | A04
| B04 | [11 empty] | B04
| C04 | [11 empty] | C04
| D04 | [11 empty] | D04
| A05 | [11 empty] | A05
| B05 | [11 empty] | B05
| C05 | [11 empty] | C05
| D05 | [11 empty] | D05
| A06 | [11 empty] | A06
| B06 | [11 empty] | B06
| C06 | [11 empty] | C06
| D06 | [11 empty] | D06
| A07 | [11 empty] | A07
| B07 | [11 empty] | B07
| C07 | [11 empty] | C07
| D07 | [11 empty] | D07
| A08 | [11 empty] | A08
| B08 | [11 empty] | B08
| C08 | [11 empty] | C08
| D08 | [11 empty] | D08
| A09 | [11 empty] | A09
| B09 | [11 empty] | B09
| C09 | [11 empty] | C09
| D09 | [11 empty] | D09
| A10 | [11 empty] | A10
| B10 | [11 empty] | B10
| C10 | [11 empty] | C10
| D10 | [11 empty] | D10
| A11 | [11 empty] | A11
| B11 | [11 empty] | B11
| C11 | [11 empty] | C11
| D11 | [11 empty] | D11
5mm! | A12 | [10 empty] | 5 | A12
5mm! | B12 | [10 empty] | 5 | B12
5mm! | C12 | [10 empty] | 5 | C12
5mm! | D12 | [10 empty] | 5 | D12
| A13 | [11 empty] | A13
| B13 | [11 empty] | B13
| C13 | [11 empty] | C13
| D13 | [11 empty] | D13
| A14 | [11 empty] | A14
| B14 | [11 empty] | B14
| C14 | [11 empty] | C14
| D14 | [11 empty] | D14
| A15 | [11 empty] | A15
| B15 | [11 empty] | B15
| C15 | [11 empty] | C15
| D15 | [11 empty] | D15
| A16 | [11 empty] | A16
| B16 | [11 empty] | B16
| C16 | [11 empty] | C16
| D16 | [11 empty] | D16
| A17 | [11 empty] | A17
| B17 | [11 empty] | B17
| C17 | [11 empty] | C17
| D17 | [11 empty] | D17
| A18 | [11 empty] | A18
| B18 | [11 empty] | B18
| C18 | [11 empty] | C18
| D18 | [11 empty] | D18
| A19 | [11 empty] | A19
| B19 | [11 empty] | B19
| C19 | [11 empty] | C19
| D19 | [11 empty] | D19
| A20 | [11 empty] | A20
| B20 | [11 empty] | B20
| C20 | [11 empty] | C20
| D20 | [11 empty] | D20
5mm! | A21 | [10 empty] | 5 | A21
5mm! | B21 | [10 empty] | 5 | B21
5mm! | C21 | [10 empty] | 5 | C21
5mm! | D21 | [10 empty] | 5 | D21
| A22 | [11 empty] | A22
| B22 | [11 empty] | B22
| C22 | [11 empty] | C22
| D22 | [11 empty] | D22
| A23 | [11 empty] | A23
| B23 | [11 empty] | B23
| C23 | [11 empty] | C23
| D23 | [11 empty] | D23
| A24 | [11 empty] | A24
| B24 | [11 empty] | B24
| C24 | [11 empty] | C24
| D24 | [11 empty] | D24
| A25 | [11 empty] | A25
| B25 | [11 empty] | B25
| C25 | [11 empty] | C25
| D25 | [11 empty] | D25
| A26 | [11 empty] | A26
| B26 | [11 empty] | B26
| C26 | [11 empty] | C26
| D26 | [11 empty] | D26
| A27 | [11 empty] | A27
| B27 | [11 empty] | B27
| C27 | [11 empty] | C27
| D27 | [11 empty] | D27
| A28 | [11 empty] | A28
| B28 | [11 empty] | B28
| C28 | [11 empty] | C28
| D28 | [11 empty] | D28
| A29 | [11 empty] | A29
| B29 | [11 empty] | B29
| C29 | [11 empty] | C29
| D29 | [11 empty] | D29
| A30 | [11 empty] | A30
| B30 | [11 empty] | B30
| C30 | [11 empty] | C30
| D30 | [11 empty] | D30
| A31 | [11 empty] | A31
| B31 | [11 empty] | B31
| C31 | [11 empty] | C31
| D31 | [11 empty] | D31
| A32 | [11 empty] | A32
| B32 | [11 empty] | B32
| C32 | [11 empty] | C32
| D32 | [11 empty] | D32
| A33 | [11 empty] | A33
| B33 | [11 empty] | B33
| C33 | [11 empty] | C33
| D33 | [11 empty] | D33
| A34 | [11 empty] | A34
| B34 | [11 empty] | B34
| C34 | [11 empty] | C34
| D34 | [11 empty] | D34
Ring Joint Verification Notes
Note 1
A complete check of the vertical reinforcement joints inculdes:
No interference with Tubes,
No interference with ring joint thicknesses,
Verification of correct bolt-hole alignment (petal-to-tube-to-petal)
Note 2
A complete check of the platform connection joints inculdes:
No interference with Tubes,
No interference with ring joint thicknesses,
No interference with moire
Verification of correct bolt-hole alignment (Column element to base plate)

## Rib Moire & Triangle models
Rib Moire and Triangle Joint Modle Check List (pls. use your initials)
Rib | Verify ring joint-to-rib match (both sides) | Verify no overlapping of text | Verifty Tirangle joint Lableing on rib is correct | Moire | Verify moire splice labels match and positioning works | Verify triangle-to-moire match | Triangle Joint | Verfity moire-triangle-rib labeling matches.
A00A01 |  |  |  | 1 |  |  | 1
A01A02 |  |  |  | 2 |  |  | 2
A02A03 |  |  |  | 3 |  |  | 3
A03A04 |  |  |  | 4 |  |  | 4
A04A05 |  |  |  | 5 |  |  | 5
A05A06 |  |  |  | 6 |  |  | 6
A06A07 |  |  |  | 7 |  |  | 7
A07A08 |  |  |  | 8 |  |  | 8
A08A09 |  |  |  | 9 |  |  | 9
A09A10 |  |  |  | 10 |  |  | 10
A10A11 |  |  |  | 11 |  |  | 11
A11A12 |  |  |  | 12 |  |  | 12
A12A13 |  |  |  | 13 |  |  | 13
A13A14 |  |  |  | 14 |  |  | 14
A14A15 |  |  |  | 15 |  |  | 15
A15A16 |  |  |  | 16 |  |  | 16
A16A17 |  |  |  | 17 |  |  | 17
A17A18 |  |  |  | 18 |  |  | 18
A18A19 |  |  |  | 19 |  |  | 19
A19A20 |  |  |  | 20 |  |  | 20
A20A21 |  |  |  | 21 |  |  | 21
A21A22 |  |  |  | 22 |  |  | 22
A22A23 |  |  |  | 23 |  |  | 23
A23A24 |  |  |  | 24 |  |  | 24
A24A25 |  |  |  | 25 |  |  | 25
A25A26 |  |  |  | 26 |  |  | 26
A26A27 |  |  |  | 27 |  |  | 27
A27A28 |  |  |  | 28 |  |  | 28
A28A29 |  |  |  | 29 |  |  | 29
A29A30 |  |  |  | 30 |  |  | 30
A30A31 |  |  |  | 31 |  |  | 31
A31A32 |  |  |  | 32 |  |  | 32
A32A33 |  |  |  | 33 |  |  | 33
A33A34 |  |  |  | 34 |  |  | 34
A34A00 |  |  |  | 35 |  |  | 35
B00B01 |  |  |  | 36 |  |  | 36
B01B02 |  |  |  | 37 |  |  | 37
B02B03 |  |  |  | 38 |  |  | 38
B03B04 |  |  |  | 39 |  |  | 39
B04B05 |  |  |  | 40 |  |  | 40
B05B06 |  |  |  | 41 |  |  | 41
B06B07 |  |  |  | 42 |  |  | 42
B07B08 |  |  |  | 43 |  |  | 43
B08B09 |  |  |  | 44 |  |  | 44
B09B10 |  |  |  | 45 |  |  | 45
B10B11 |  |  |  | 46 |  |  | 46
B11B12 |  |  |  | 47 |  |  | 47
B12B13 |  |  |  | 48 |  |  | 48
B13B14 |  |  |  | 49 |  |  | 49
B14B15 |  |  |  | 50 |  |  | 50
B15B16 |  |  |  | 51 |  |  | 51
B16B17 |  |  |  | 52 |  |  | 52
B17B18 |  |  |  | 53 |  |  | 53
B18B19 |  |  |  | 54 |  |  | 54
B19B20 |  |  |  | 55 |  |  | 55
B20B21 |  |  |  | 56 |  |  | 56
B21B22 |  |  |  | 57 |  |  | 57
B22B23 |  |  |  | 58 |  |  | 58
B23B24 |  |  |  | 59 |  |  | 59
B24B25 |  |  |  | 60 |  |  | 60
B25B26 |  |  |  | 61 |  |  | 61
B26B27 |  |  |  | 62 |  |  | 62
B27B28 |  |  |  | 63 |  |  | 63
B28B29 |  |  |  | 64 |  |  | 64
B29B30 |  |  |  | 65 |  |  | 65
B30B31 |  |  |  | 66 |  |  | 66
B31B32 |  |  |  | 67 |  |  | 67
B32B33 |  |  |  | 68 |  |  | 68
B33B34 |  |  |  | 69 |  |  | 69
B34B00 |  |  |  | 70 |  |  | 70
C00C01 |  |  |  | 71 |  |  | 71
C01C02 |  |  |  | 72 |  |  | 72
C02C03 |  |  |  | 73 |  |  | 73
C03C04 |  |  |  | 74 |  |  | 74
C04C05 |  |  |  | 75 |  |  | 75
C05C06 |  |  |  | 76 |  |  | 76
C06C07 |  |  |  | 77 |  |  | 77
C07C08 |  |  |  | 78 |  |  | 78
C08C09 |  |  |  | 79 |  |  | 79
C09C10 |  |  |  | 80 |  |  | 80
C10C11 |  |  |  | 81 |  |  | 81
C11C12 |  |  |  | 82 |  |  | 82
C12C13 |  |  |  | 83 |  |  | 83
C13C14 |  |  |  | 84 |  |  | 84
C14C15 |  |  |  | 85 |  |  | 85
C15C16 |  |  |  | 86 |  |  | 86
C16C17 |  |  |  | 87 |  |  | 87
C17C18 |  |  |  | 88 |  |  | 88
C18C19 |  |  |  | 89 |  |  | 89
C19C20 |  |  |  | 90 |  |  | 90
C20C21 |  |  |  | 91 |  |  | 91
C21C22 |  |  |  | 92 |  |  | 92
C22C23 |  |  |  | 93 |  |  | 93
C23C24 |  |  |  | 94 |  |  | 94
C24C25 |  |  |  | 95 |  |  | 95
C25C26 |  |  |  | 96 |  |  | 96
C26C27 |  |  |  | 97 |  |  | 97
C27C28 |  |  |  | 98 |  |  | 98
C28C29 |  |  |  | 99 |  |  | 99
C29C30 |  |  |  | 100 |  |  | 100
C30C31 |  |  |  | 101 |  |  | 101
C31C32 |  |  |  | 102 |  |  | 102
C32C33 |  |  |  | 103 |  |  | 103
C33C34 |  |  |  | 104 |  |  | 104
C34C00 |  |  |  | 105 |  |  | 105
D00D01 |  |  |  | 106 |  |  | 106
D01D02 |  |  |  | 107 |  |  | 107
D02D03 |  |  |  | 108 |  |  | 108
D03D04 |  |  |  | 109 |  |  | 109
D04D05 |  |  |  | 110 |  |  | 110
D05D06 |  |  |  | 111 |  |  | 111
D06D07 |  |  |  | 112 |  |  | 112
D07D08 |  |  |  | 113 |  |  | 113
D08D09 |  |  |  | 114 |  |  | 114
D09D10 |  |  |  | 115 |  |  | 115
D10D11 |  |  |  | 116 |  |  | 116
D11D12 |  |  |  | 117 |  |  | 117
D12D13 |  |  |  | 118 |  |  | 118
D13D14 |  |  |  | 119 |  |  | 119
D14D15 |  |  |  | 120 |  |  | 120
D15D16 |  |  |  | 121 |  |  | 121
D16D17 |  |  |  | 122 |  |  | 122
D17D18 |  |  |  | 123 |  |  | 123
D18D19 |  |  |  | 124 |  |  | 124
D19D20 |  |  |  | 125 |  |  | 125
D20D21 |  |  |  | 126 |  |  | 126
D21D22 |  |  |  | 127 |  |  | 127
D22D23 |  |  |  | 128 |  |  | 128
D23D24 |  |  |  | 129 |  |  | 129
D24D25 |  |  |  | 130 |  |  | 130
D25D26 |  |  |  | 131 |  |  | 131
D26D27 |  |  |  | 132 |  |  | 132
D27D28 |  |  |  | 133 |  |  | 133
D28D29 |  |  |  | 134 |  |  | 134
D29D30 |  |  |  | 135 |  |  | 135
D30D31 |  |  |  | 136 |  |  | 136
D31D32 |  |  |  | 137 |  |  | 137
D32D33 |  |  |  | 138 |  |  | 138
D33D34 |  |  |  | 139 |  |  | 139
D34D00 |  |  |  | 140 |  |  | 140
|  |  |  | 141 |  |  | 141
|  |  |  | 142 |  |  | 142
|  |  |  | 143 |  |  | 143
|  |  |  | 144 |  |  | 144
|  |  |  | 145 |  |  | 145
|  |  |  | 146 |  |  | 146
|  |  |  | 147 |  |  | 147
|  |  |  | 148 |  |  | 148
|  |  |  | 149 |  |  | 149
|  |  |  | 150 |  |  | 150
|  |  |  | 151 |  |  | 151
|  |  |  | 152 |  |  | 152
|  |  |  | 153 |  |  | 153
|  |  |  | 154 |  |  | 154
|  |  |  | 155 |  |  | 155
|  |  |  | 156 |  |  | 156
|  |  |  | 157 |  |  | 157
|  |  |  | 158 |  |  | 158
|  |  |  | 159 |  |  | 159
|  |  |  | 160 |  |  | 160
|  |  |  | 161 |  |  | 161
|  |  |  | 162 |  |  | 162
|  |  |  | 163 |  |  | 163
|  |  |  | 164 |  |  | 164
|  |  |  | 165 |  |  | 165
|  |  |  | 166 |  |  | 166
|  |  |  | 167 |  |  | 167
|  |  |  | 168 |  |  | 168
|  |  |  | 169 |  |  | 169
|  |  |  | 170 |  |  | 170
|  |  |  | 171 |  |  | 171
|  |  |  | 172 |  |  | 172
|  |  |  | 173 |  |  | 173
|  |  |  | 174 |  |  | 174
|  |  |  | 175 |  |  | 175
|  |  |  | 176 |  |  | 176
|  |  |  | 177 |  |  | 177
|  |  |  | 178 |  |  | 178
|  |  |  | 179 |  |  | 179
|  |  |  | 180 |  |  | 180
|  |  |  | 181 |  |  | 181
|  |  |  | 182 |  |  | 182
|  |  |  | 183 |  |  | 183
|  |  |  | 184 |  |  | 184
|  |  |  | 185 |  |  | 185
|  |  |  | 186 |  |  | 186
|  |  |  | 187 |  |  | 187
|  |  |  | 188 |  |  | 188
|  |  |  | 189 |  |  | 189
|  |  |  | 190 |  |  | 190
|  |  |  | 191 |  |  | 191
|  |  |  | 192 |  |  | 192
|  |  |  | 193 |  |  | 193
|  |  |  | 194 |  |  | 194
|  |  |  | 195 |  |  | 195
|  |  |  | 196 |  |  | 196
|  |  |  | 197 |  |  | 197
|  |  |  | 198 |  |  | 198
|  |  |  | 199 |  |  | 199
|  |  |  | 200 |  |  | 200
|  |  |  | 201 |  |  | 201
|  |  |  | 202 |  |  | 202
|  |  |  | 203 |  |  | 203
|  |  |  | 204 |  |  | 204
|  |  |  | 205 |  |  | 205
|  |  |  | 206 |  |  | 206
|  |  |  | 207 |  |  | 207
|  |  |  | 208 |  |  | 208
|  |  |  | 209 |  |  | 209
|  |  |  | 210 |  |  | 210
|  |  |  | 211 |  |  | 211
|  |  |  | 212 |  |  | 212
|  |  |  | 213 |  |  | 213
|  |  |  | 214 |  |  | 214
|  |  |  | 215 |  |  | 215
|  |  |  | 216 |  |  | 216
|  |  |  | 217 |  |  | 217
|  |  |  | 218 |  |  | 218
|  |  |  | 219 |  |  | 219
|  |  |  | 220 |  |  | 220
|  |  |  | 221 |  |  | 221
|  |  |  | 222 |  |  | 222
|  |  |  | 223 |  |  | 223
|  |  |  | 224 |  |  | 224
|  |  |  | 225 |  |  | 225
|  |  |  | 226 |  |  | 226
|  |  |  | 227 |  |  | 227
|  |  |  | 228 |  |  | 228
|  |  |  | 229 |  |  | 229
|  |  |  | 230 |  |  | 230
|  |  |  | 231 |  |  | 231
|  |  |  | 232 |  |  | 232
|  |  |  | 233 |  |  | 233
|  |  |  | 234 |  |  | 234
|  |  |  | 235 |  |  | 235
|  |  |  | 236 |  |  | 236
|  |  |  | 237 |  |  | 237
|  |  |  | 238 |  |  | 238
|  |  |  | 239 |  |  | 239
|  |  |  | 240 |  |  | 240
|  |  |  | 241 |  |  | 241
|  |  |  | 242 |  |  | 242
|  |  |  | 243 |  |  | 243
|  |  |  | 244 |  |  | 244
|  |  |  | 245 |  |  | 245
|  |  |  | 246 |  |  | 246
|  |  |  | 247 |  |  | 247
|  |  |  | 248 |  |  | 248
|  |  |  | 249 |  |  | 249
|  |  |  | 250 |  |  | 250
|  |  |  | 251 |  |  | 251
|  |  |  | 252 |  |  | 252
|  |  |  | 253 |  |  | 253
|  |  |  | 254 |  |  | 254
|  |  |  | 255 |  |  | 255
|  |  |  | 256 |  |  | 256
|  |  |  | 257 |  |  | 257
|  |  |  | 258 |  |  | 258
|  |  |  | 259 |  |  | 259
|  |  |  | 260 |  |  | 260
|  |  |  | 261 |  |  | 261
|  |  |  | 262 |  |  | 262
|  |  |  | 263 |  |  | 263
|  |  |  | 264 |  |  | 264
|  |  |  | 265 |  |  | 265
|  |  |  | 266 |  |  | 266
|  |  |  | 267 |  |  | 267
|  |  |  | 268 |  |  | 268
|  |  |  | 269 |  |  | 269
|  |  |  | 270 |  |  | 270
|  |  |  | 271 |  |  | 271
|  |  |  | 272 |  |  | 272
|  |  |  | 273 |  |  | 273
|  |  |  | 274 |  |  | 274
|  |  |  | 275 |  |  | 275
|  |  |  | 276 |  |  | 276
|  |  |  | 277 |  |  | 277
|  |  |  | 278 |  |  | 278
|  |  |  | 279 |  |  | 279
|  |  |  | 280 |  |  | 280
|  |  |  | 281 |  |  | 281
|  |  |  | 282 |  |  | 282
|  |  |  | 283 |  |  | 283
|  |  |  | 284 |  |  | 284
|  |  |  | 285 |  |  | 285
|  |  |  | 286 |  |  | 286
|  |  |  | 287 |  |  | 287
|  |  |  | 288 |  |  | 288
|  |  |  | 289 |  |  | 289
|  |  |  | 290 |  |  | 290
|  |  |  | 291 |  |  | 291
|  |  |  | 292 |  |  | 292
|  |  |  | 293 |  |  | 293
|  |  |  | 294 |  |  | 294
|  |  |  | 295 |  |  | 295
|  |  |  | 296 |  |  | 296
|  |  |  | 297 |  |  | 297
|  |  |  | 298 |  |  | 298
|  |  |  | 299 |  |  | 299
|  |  |  | 300 |  |  | 300
|  |  |  | 301 |  |  | 301
|  |  |  | 302 |  |  | 302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425
426
427
428
429
430
431
432
433
434
435
436
437
438
439
440
441
442
443
444
445
446
447
448
449
450
451
452
453
454
455
456
457
458
459
460
461
462
463
464
465
466
467
468
469
470
471
472
473
474
475
476
477
478
479
480
481
482
483
484
485
486
487
488
489
490
491
492
493
494
495
496
497
498
499
500
501
502
503
504
505
506
507
508
509
510
511
512
513
514
515
516
517
518
519
520
521
522
523
524
525
526
527
528
529
530
531
532
533
534
535
536
537
538
539
540
541
542
543
544
545
546
547
548
549
550
551
552
553
554
555
556
557
558
559
560
561
562
563
564
565
566
567
568
569
570
571
572
573
574
575
576
577
578
579
580
581
582
583
584
585
586
587
588
589
590
591
592
593
594
595
596
597
598
599
600
601
602
603
604
605
606
607
608
609
610
611
612
613
614
615
616
617
618
619
620
621
622
623
624
625
626
627
628
629
630
631
632
633
634
635
636
637
638
639
640
641
642
643
644
645
646
647
648
649
650
651
652
653
654
655
656
657
658
659
660
661
662
663
664
665
666
667
668
669
670
671
672
673
674
675
676
677
678
679
680
681
682
683
684
685
686
687
688
689
690
691
692
693
694
695
696
697
698
699
700
701
702
703
704
705
706
707
708
709
710
711
712
713
714
715
716
717
718
719
720
721
722
723
724
725
726
727
728
729
730
731
732
733
734
735
736
737
738
739
740
741
742
743
744
745
746
747
748
749
750
751
752
753
754
755
756
757
758
759
760
761
762
763
764
765
766
767
768
769
770
771
772
773
774
775
776
777
778
779
780
781
782
783
784
785
786
787
788
789
790
791
792
793
794
795
796
797
798
799
800
801
802
803
804
805
806
807
808
809
810
811
812
813
814
815
816
817
818
819
820
821
822
823
824
825
826
827
828
829
830
831
832
833
834
835
836
837
838
839
840
841
842
843
844
845
846
847
848
849
850
851
852
853
854
855
856
857
858
859
860
861
862
863
864
865
866
867
868
869
870
871
872
873
874
875
876
877
878
879
880
881
882
883
884
885
886
887
888
889
890
891
892
893
894
895
896
897
898
899
900
901
902
903
904
905
906
907
908
909
910
911
912
913
914
915
916
917
918
919
920
921
922
923
924
925
926
927
928
929
930
931
932
933
934
935
936
937
938
939
940
941
942
943
944
945
946
947
948
949
950
951
952
953
954
955
956
957
958
959
960
961
962
963
964
965
966
967
968
969
970
971
972
973
974
975
976
977
978
979
980
981
982
983
984
985
986
987
988
989
990
991
992
993
994
995
996
997
998
999
1000
1001
1002
1003
1004
1005
1006
1007
1008
1009
1010
1011
1012
1013
1014
1015
1016
1017
1018
1019
1020
1021
1022
1023
1024
1025
1026
1027
1028
1029
1030
1031
1032
1033
1034
1035
1036
1037
1038
1039
1040
1041
1042
1043
1044
1045
1046
1047
1048
1049
1050
1051
1052
1053
1054
1055
1056
1057
1058
1059
1060
1061
1062
1063
1064
1065
1066
1067
1068
1069
1070
1071
1072
1073
1074
1075
1076
1077
1078
1079
1080
1081
1082
1083
1084
1085
1086
1087
1088
1089
1090
1091
1092
1093
1094
1095
1096
1097
1098
1099
1100
1101
1102
1103
1104
1105
1106
1107
1108
1109
1110
1111
1112
1113
1114
1115
1116
1117
1118
1119
1120
1121
1122
1123
1124
1125
1126
1127
1128
1129
1130
1131
1132
1133
1134
1135
1136
1137
1138
1139
1140
1141
1142
1143
1144
1145
1146
1147
1148
1149
1150
1151
1152
1153
1154
1155
1156
1157
1158
1159
1160
1161
1162
1163
1164
1165
1166
1167
1168
1169
1170
1171
1172
1173
1174
1175
1176
1177
1178
1179
1180
1181
1182
1183
1184
1185
1186
1187
1188
1189
1190
1191
1192
1193
1194
1195
1196
1197
1198
1199
1200
1201
1202
1203
1204
1205
1206
1207
1208

## Platform Check List
| Platform | ü
1
1
3
4
5
5
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140